## Overall
TimbreTool Project Breakdown - Overall Tasks

Start date:	22/05/2020
Daily working slot / min:	90

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
A	Ongoing research	21	-	16/06/2020	n
B	Define concepts	4	A	20/06/2020	n
C	Controller UI design		B		n
D	Controller implementation		C		n
E	Controller testing		D		n
F	Interface UI design		A, B		n
G	Interface implementation		E, F		n
H	Interface testing		G		n
I	Release		E, H		n
J	Retirement		I		n

## A
Ongoing Research

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)	Notes
A1	Filtering & FFT	2	-	24/05/2020	y	Notemaking and choice of algorithms
A1.5	FFT dry run in JUCE	2	A1	26/05/2020	n	Made a non-functioning prototype to practice the JUCE framework core modules, will need to make another featuring an FFT
A2	Pitch & rhythm recognition	2	-	28/05/2020	y
A3	Envelopes	2	-	30/05/2020	y
A5	Loading data from files	2	-	31/05/2020	y	Experimented with loading data into an AudioBuffer
A6	AWS hosting and data connectivity	4	A5	04/06/2020	n
A7	JUCE libraries needed	1	A1-A5	05/06/2020	n	Started on file reading
A8	JavaScript libraries needed	1	A1-A7	05/06/2020	n
A9	Needs of producers and engineers	2	-	06/06/2020	n
A10	UI design survey	2	A9	10/06/2020	y	Survey uploaded, waiting on responses
A11	Design scheme of similar programs	1	-	06/06/2020	n

## B
Define Concepts

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
B1	Background	2	-	14/06/2020	n
B2	Processing ideas	2	-	16/06/2020	n

## C
Controller UI Design

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
C1	User analysis & requirements
C2

## D
Controller Implementation

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## E
Controller Testing

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## F
Interface UI Design

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## G
Interface Implementation

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## H
Interface Testing

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## I
Release

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements

## J
Retirement

Task ID	Task	Duration / slots	Depends on	Deadline	Done? (Y/N)
	User analysis & requirements